## 3 Alpha Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | Milestone Review | Not having a working build pushed to the milestone builds folder of the repo before the day of the milestone review is unacceptable. - All teams must have a zipped exe build in the “Milestone builds” folder - We aren’t working on user stories during class time on the day of the milestone - We aren’t integrating the builds during class time on the day of the milestone Previous sprint review - Finalize Trello board - - All user stories in final categories - - Hours spent on all tasks entered - Discus work problems if there were any - - If a user story estimate was off why was it off? Next sprint planning - Sprint goal must be understood - User stories moved from product backlog to sprint backlog that supports the sprint goal - Test cases and task lists reviewed for all sprint user stories Story allocation - Planning poker completed for all stories - User story owners assigned for all stories - Sprint plan reviewed and accepted by CD before the end of the lab It is Highly suggested that the team perform a code freeze no later then 4 hours before the milestone needs to be submitted. Code freeze: A time where no changes whatsoever are permitted to the program's source code used to maintain ensure the quality and integrity of the build. - Before each milestone and sprint end, a final integration is needed. - - Forces an integration at a safe time - - Ensures there is time for testing and validation of the build - - Confirm sprint goals - - Peer check each other’s work |  | 2022-08-10 23:59 |  |  | 1 | https://trello.com/c/g6WAtA9O
Important Notes | Team's agreed upon schedule | The team should agree upon a schedule when and where they will be meeting up outside of class time and document those times and places onto this card. |  |  |  |  | 4 | https://trello.com/c/CvNEvhqy
Incomplete | Parachute Ability | Add parachute ability to player - on activation parachute asset displays above player character and a glide effect happens - slowly allowing player to traverse more vertical areas smoothly and without fear of fall damage | 8 |  |  | Unplanned Work | 43 | https://trello.com/c/GlNR3YSD
Partially Complete | Mini Map | UI component to show player level as a whole | 1 |  | RW,T | Unplanned Work | 11 | https://trello.com/c/w40HXWNB
Partially Complete | No warnings or errors in the code base | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. | 0.5 |  | KT,T | TRC Requirement | 7 | https://trello.com/c/bANWCvI7
Partially Complete | Change options in the game | Intent: - Allow the end users to change the settings for music and SFX volume Note on implementation: - The easiest way to implement this is through setting up mixer groups and then routing the various audio sources in the game through the right mixer group (https://docs.unity3d.com/Manual/AudioMixer.html). An issue from mixer groups though is that they take volume in Db rather than a scaler 0 to 1 so it has to be converted. To roughly convert from a scaler value of 0-1 into logarithmic value for the unity mixer group is to use "Mathf.Log10(volume) * 20" Note on estimation: - Creating the menu doesn't take long. the difficulty and time involved on this one is in getting the mixer groups integrated in all of the audio sources in the game | 8 |  | JD,T | TRC Requirement,High Priority | 5 | https://trello.com/c/Bk4mrFNc
Partially Complete | Boss Enemy | A boss for the final level | 5 |  | JD,T | High Priority | 9 | https://trello.com/c/8stVNC72
Complete (Done) | Technical Debt - Bomb Timer | Bomb timer needs to be fixed | 0.5 |  | RW | High Priority | 28 | https://trello.com/c/6pJW5XGU
Complete (Done) | Loading Screen Functionality | Is there functionality for a load screen to be displayed during load times? A placeholder is fine for this for now, as long as the functionality of it works. | 8 |  | RW | Medium Priority | 12 | https://trello.com/c/JOJV1sgO
Complete (Done) | Defusing | Bombs should be able to be defused | 1 |  | RW | High Priority | 19 | https://trello.com/c/lYySdCBF
Complete (Done) | Audio feedback on the menus | Intent: - Inform the user that the input was entered | 1 |  | RW | TRC Requirement,Low Priority | 12 | https://trello.com/c/rpvrZvyA
Complete (Done) | Background music for the menus and levels | Intent: - Create ambiance and emotional tone for the game and levels. | 2 |  | RW | TRC Requirement,Difficulty: Easy | 13 | https://trello.com/c/MnpymBFC
Complete (Done) | Death state for bombs | Update death state for bombs | 1 |  | RW | High Priority | 20 | https://trello.com/c/Wr0qd3nK
Complete (Done) | Technical Debt - Pickups | Pickups dont always activate reliably when running over them. | 1 |  | RW | High Priority | 32 | https://trello.com/c/1IFNsZ98
Complete (Done) | Raymond - Technical Debt - Codebase commenting | Comment your code | 0.5 |  | RW | High Priority | 38 | https://trello.com/c/JJBTs0Lc
Complete (Done) | Level Transitions | Can you transition smoothly to other scenes/levels while in play mode? | 13 |  | RW,KT | Medium Priority | 17 | https://trello.com/c/rSbplRQn
Complete (Done) | Audio Changes | Updates to games audio clips | 3 |  | KT | High Priority | 27 | https://trello.com/c/pS6PVkt2
Complete (Done) | Functionality for lose game cutscene | When losing the game does a cutscene play ? | 1 |  | KT | Medium Priority | 24 | https://trello.com/c/UIXWjjVM
Complete (Done) | Functionality for winning cutscene | When beating the game, a cutscene should be played for the user. This card is for the functionality of that happening, not the video itself. | 1 |  | KT | Medium Priority | 23 | https://trello.com/c/jQ7vs8iN
Complete (Done) | Keyboard and mouse for the game's menus | Intent: - Create control structure allowing keyboard and mouse to be used for all of the game's menus Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. | 8 |  | KT | TRC Requirement,Medium Priority | 9 | https://trello.com/c/IVSp7gAs
Complete (Done) | Functionality for opening cutscene | When starting a new game, a cutscene should be played for the user. This card is for the functionality of that happening, not the video itself. | 1 |  | KT | Medium Priority | 22 | https://trello.com/c/SpCvuYPV
Complete (Done) | Control Display for Pause Menu | Display all controls for the game and allow player to go back to pause menu | 1 |  | KT | Low Priority | 45 | https://trello.com/c/4ILuTx1l
Complete (Done) | IPM Document | A plotting of the challenges the user faces while playing a game, against the time that that user has used the product. Notes on estimation: - This done as a team usually involves a couple hours of discussion as long as the mechanics of the game have been fully defined during pre production | 8 |  | KT | High Priority | 6 | https://trello.com/c/9pxFTVCU
Complete (Done) | Kelsey - Technical Debt - Codebase commenting | Comment your code | 0.5 |  | KT | High Priority | 37 | https://trello.com/c/dczO03Ml
Complete (Done) | HUD Changes | Changes to player hud | 2 |  | KT | Difficulty: Easy | 13 | https://trello.com/c/y7RPrOHN
Complete (Done) | Technical Debt - Prefab Postions | Prefab transform->positions needs to be zero'd out | 0.5 |  | KT,T | High Priority | 31 | https://trello.com/c/I7p5yiD8
Complete (Done) | Object Scaling | Do all of the enemies and objects present feel in scale with eachother? Often helps to agree on a single object to base scaling on/to compare other objects to. | 3 |  | KT,T | Low Priority | 18 | https://trello.com/c/5N8rJoet
Complete (Done) | Technical Debt - Audio Bugs | All audio should be efficient and different | 0.5 |  | T,KT | High Priority | 26 | https://trello.com/c/tb7PNUM6
Complete (Done) | Player Shotgun Weapon | Add shotgun for players multiple weapon choices | 5 |  | T | Medium Priority | 6 | https://trello.com/c/GQPrPSHu
Complete (Done) | Player Sniper Rifle Weapon | add player weapon for sniper rifle - including UI/camera changes for zoom feature | 13 |  | T | Medium Priority | 42 | https://trello.com/c/g0CGaBa8
Complete (Done) | Boss Enemy | created a new boss since the other one didnt work | 2 |  | T | High Priority | 46 | https://trello.com/c/QHwjQDIf
Complete (Done) | FPS guns going through walls fix | Fix the bug where guns pass through environment objects This can easily be fixed by adding a second camera to the player that renders only the layer containing the player and the player's weapons/items https://youtu.be/wH4IyFXrWQw | 0.5 |  | T | Difficulty: Easy | 1 | https://trello.com/c/pVyT7Vax
Complete (Done) | Player Grenade | Player should be able shoot grenades | 2 |  | T | Medium Priority | 2 | https://trello.com/c/uYZCLWIt
Complete (Done) | Showcase Level | A level that can be loaded with a debug menu button or debug key check that shows all of the created features in sequence. This would not be a level the users would ever see, just a space that proves the functionality works in an easily accessible way. This will be removed later for the final builds. | 0.5 |  | T | High Priority | 14 | https://trello.com/c/sepOxsFG
Complete (Done) | Player Dodge | Player should be able to dodge | 3 |  | T | Low Priority | 8 | https://trello.com/c/qHufuDyV
Complete (Done) | Completion scenario (winning the game, achieving achievements, high score) | Intent: - Create the win condition and all of the experience we intend to provide with it Notes on estimation: - Creating the trigger for a win screen is very fast and easy, presenting the actual win scenario of the game can vary in difficulty and time necessary based on how what will be done when the player wins | 3 |  | T | Medium Priority | 2 | https://trello.com/c/ZFq62byr
Complete (Done) | Player Weapon Choices | Player should be able to use different types of weapons | 1 |  | T | Medium Priority | 3 | https://trello.com/c/W7nKVypG
Complete (Done) | Player Assault Rifle Weapon | Add assault rifle choice | 2 |  | T | Medium Priority | 5 | https://trello.com/c/A5leWb8h
Complete (Done) | Player Pistol Weapon (Default) | update the player pistol to match new system of multiple weapon choices | 0.5 |  | T | Medium Priority | 4 | https://trello.com/c/3DGu3l0E
Complete (Done) | Tyler - Technical Debt - Codebase commenting | Comment your code | 0.5 |  | T | High Priority | 41 | https://trello.com/c/bWju947z
Complete (Done) | Technical Debt - Controls | Do the controls do the appropriate action? | 0 |  | T | High Priority | 29 | https://trello.com/c/xlid6I35
Complete (Done) | Traps | Do some levels contain traps? | 8 |  | JD | Medium Priority | 16 | https://trello.com/c/Cy3YoAFI
Complete (Done) | Jose - Technical Debt - Codebase commenting | Comment your code | 0.5 |  | JD | High Priority | 40 | https://trello.com/c/cPmnAQuQ
Complete (Done) | Tutorial Level | Level that shows player how to play the game | 3 |  | CL | Medium Priority | 15 | https://trello.com/c/ZRIUAt5v
Complete (Done) | Player Weapon Feedback | Gun response to firing/camera movement | 8 |  | CL | High Priority | 7 | https://trello.com/c/U4Rixikl
Complete (Done) | Defuse Animation | There should be an animation that shows when the player defusing bomb | 3 |  | CL | Medium Priority | 21 | https://trello.com/c/rAkX7avd
Complete (Done) | Spawner Amount | Appropriate amount of enemies spawn when player triggers spawner | 2 |  | CL | High Priority | 14 | https://trello.com/c/QRkkVVig
Complete (Done) | Technical Debt - Spawner Bugs | Issues with the spawner need to be fixed | 3 |  | CL | High Priority | 30 | https://trello.com/c/6DxHbq0J
Complete (Done) | Navigate the main menu | Intent: - Create functionality for the main menu Note on estimation: - This is generally a very quick task since it is just the functionality of the menu (not final visuals) | 5 |  | CL | TRC Requirement,High Priority | 10 | https://trello.com/c/oKbvMF7p
Complete (Done) | Collin - Technical Debt - Codebase commenting | Comment your code | 0.5 |  | CL | High Priority | 39 | https://trello.com/c/GxvolNPz
Complete (Done) | Technical Debt - Player dies | Player dead bugs | 8 |  | CL | High Priority | 25 | https://trello.com/c/Rlhe8dmK
Complete (Done) | Ability to pause the game | Intent: - Allow the user to stop playing the game momentarily |  |  |  | TRC Requirement | 8 | https://trello.com/c/DqvqNDhR
Complete (Done) | Loss condition and it is clear to the user when and how they lost | Intent: - Create loss condition and player feedback involved in it |  |  |  |  | 3 | https://trello.com/c/4rY0MRPV
Complete (Done) | Keyboard and mouse in-game | Intent: - Set up, test and use the default game controls for keyboard and mouse Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. |  |  |  | TRC Requirement | 11 | https://trello.com/c/09F95ZdN

## Archived 3 Alpha Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL