## 4 Beta Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | Milestone Review | Not having a working build pushed to the milestone builds folder of the repo before the day of the milestone review is unacceptable. - All teams must have a zipped exe build in the “Milestone builds” folder - We aren’t working on user stories during class time on the day of the milestone - We aren’t integrating the builds during class time on the day of the milestone Previous sprint review - Finalize Trello board - - All user stories in final categories - - Hours spent on all tasks entered - Discus work problems if there were any - - If a user story estimate was off why was it off? Next sprint planning - Sprint goal must be understood - User stories moved from product backlog to sprint backlog that supports the sprint goal - Test cases and task lists reviewed for all sprint user stories Story allocation - Planning poker completed for all stories - User story owners assigned for all stories - Sprint plan reviewed and accepted by CD before the end of the lab It is Highly suggested that the team perform a code freeze no later then 4 hours before the milestone needs to be submitted. Code freeze: A time where no changes whatsoever are permitted to the program's source code used to maintain ensure the quality and integrity of the build. - Before each milestone and sprint end, a final integration is needed. - - Forces an integration at a safe time - - Ensures there is time for testing and validation of the build - - Confirm sprint goals - - Peer check each other’s work |  | 2022-08-18 23:59 |  |  | 1 | https://trello.com/c/EV7B9Ip3
Important Notes | Team's agreed upon schedule | The team should agree upon a schedule when and where they will be meeting up outside of class time and document those times and places onto this card. |  |  |  |  | 16 | https://trello.com/c/b6JcIdOa
Incomplete | Cutscene Animations | Supplemental animations to replace images and text from cut scenes. | 13 |  | JW | Unplanned Work | 17 | https://trello.com/c/trGg4fvh
Complete (Done) | Play the game in a browser using WebGL | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Get the game online and playable in a browser if the game supports the web as its target platform. - If you end up having issues with memory limits this blog post goes into the details on that a bit https://blogs.unity3d.com/2016/09/20/understanding-memory-in-unity-webgl/ | 0.5 |  | CL | TRC Requirement,Target Platform,High Priority | 7 | https://trello.com/c/jUXmlwVp
Complete (Done) | Controls to function and be comfortable when playing the game on the WebGL build | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Customize the controls to be fully usable on web builds if the game supports the web player as its target platform. | 2 |  | CL | TRC Requirement,Target Platform,High Priority | 6 | https://trello.com/c/1cVmUXx2
Complete (Done) | Installer for the game | Intent: - Create an installer for the product to make it easier to distribute. Note on estimation: - There should be little time needed to complete this task, An hour or two. Installers will be created using an installer creator application. | 2 |  | CL | TRC Requirement,Medium Priority | 10 | https://trello.com/c/X9bXgmOl
Complete (Done) | Game can be played on any monitor/TV set | Intent: - Allow the game to be played on any monitor/TV set. This is testing for screen bounds images sizes and aspect ratios Note on Implementation: - Other that HUD layout, having canvas scaler components handling how each screen scales to fit aspect ratios is the main things that needs to be done to support this. Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. |  |  | CL | TRC Requirement,High Priority | 2 | https://trello.com/c/Y8iJf7u7
Complete (Done) | Credits (everyone who contributed to creating the game to get credit for their work) | Intent: - Credit everyone who contributed to the product - For outsourced assets from web portals give enough information to be able to find the source of the asset (“Asset Name by AuthorName from website.com”) Note on estimation: - Time to complete this task is heavily dependent on if we have been maintaining a list of where we got our assets from or if we need to spend time to re-find the source of the assets. | 1 |  | RW | TRC Requirement,Low Priority | 11 | https://trello.com/c/n4RR5PvF
Complete (Done) | Bug Fixes | Finding bugs and adding them here. When working on a bug add yourself as a member. Check off a bug if you fixed it. |  |  | CL |  | 18 | https://trello.com/c/yEj9lBEB
Complete (Done) | Animation for Pickups | The health and ammo pickup should float and rotate | 2 |  | RW | Low Priority | 3 | https://trello.com/c/VOTMFvik
Complete (Done) | Starting Areas | A starting area for each level where the player will spawn in | 3 |  | T | High Priority | 8 | https://trello.com/c/J1U9kTCB
Complete (Done) | Experience the game without needing to have an additional player | Intent: - Ensure all players can experience a portion of the game without the need of an additional player on an online connection. Note on estimation: - This is mostly a verification at the end of the sprint and needs little if any time dedicated to it. If an entire new mode needs to be created to support this then there should be other cards defining that mode. |  |  |  | TRC Requirement | 5 | https://trello.com/c/xMduzfn8
Complete (Done) | Play the game without needing to enable administrator mode | Intent: - Allow a larger user base by ensuring users do not need administrator access to the player the game after installation. Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. If the exe build did not ask for admin rights after saving was created on the last sprint it is unlikely that this will become an issue now. | ? |  | CL | TRC Requirement,High Priority | 3 | https://trello.com/c/RRtoaDpW
Complete (Done) | Fix load screen | Load screen needs to be updated to show actual loading process not just a set timer | 2 |  | KT | Medium Priority | 16 | https://trello.com/c/OsCfXwe7
Complete (Done) | Improvements | Make minor improvements | 6 |  | CL | High Priority | 2 | https://trello.com/c/nzrCLO8s
Complete (Done) | Debug tools removal | Intent: - Finalizing the build to prepare for the quality assurance and submission process. Note on estimation: - Usually all this involves is commenting out the lines that trigger the debug functionality. This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. | 1 |  | JD | High Priority | 12 | https://trello.com/c/pDx4IwmC
Complete (Done) | Opening cutscene | Creation of the opening cutscene | 2 |  | KT | Medium Priority | 12 | https://trello.com/c/49Lr3qIl
Complete (Done) | Player Power Ups | Enemies sometimes drop power ups for player | 13 |  | JD | Low Priority | 5 | https://trello.com/c/GycjSiCV
Complete (Done) | Closing/Win Level/Restart cutscenes | Creation of win game cutscene | 5 |  | KT | Medium Priority | 13 | https://trello.com/c/xjxoO7SA
Complete (Done) | Enemy Animation & Modeling | Enemy animation should be good quality and respond to enemy movements correctly. Enemies include Enemy 1, Enemy 2, and Enemy Grenadier | 8 |  | JD | Medium Priority | 4 | https://trello.com/c/fe2r0lpS
Complete (Done) | Maintain a frame rate of at least 30 frames per second | Intent: - Maintain a smooth and clear game experience Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. If however the game is already having issues with framerate at the point of estimating this card then the team should make their best judgement on the time to optimize where they think the slowdowns are located. | ? |  | CL | TRC Requirement,Medium Priority | 4 | https://trello.com/c/chwoeveg
Complete (Done) | No warnings or errors in the code base | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. | 8 |  | CL | TRC Requirement,Medium Priority | 13 | https://trello.com/c/rbGAK3As
Complete (Done) | Update Weapon Mechanics | Update shotgun and assault rifle weapons |  |  | T | Low Priority | 19 | https://trello.com/c/X12TIqVL
Complete (Done) | Music and Sound Effects |  | 5 |  | RW | Medium Priority | 14 | https://trello.com/c/dtbBzytJ
Complete (Done) | Level 2 | Level 2 - Defuse bombs before the timer runs out to save the city! | 13 |  | KT | High Priority | 10 | https://trello.com/c/v8OMUksq
Complete (Done) | Level 1 | Level 1 - run and kill enemies to fight your way through them to the level exit | 13 |  | RW | High Priority | 9 | https://trello.com/c/cj77aUF6
Complete (Done) | Menu system final look and functionality | Intent: - Replace all placeholder assets with final ones - Ensure quality visuals throughout the product. | 2 |  | KT | High Priority | 8 | https://trello.com/c/bAZEKkUj
Complete (Done) | Fall Damage | When falling from a high place, player takes fall damage | 3 |  | JD | Low Priority | 6 | https://trello.com/c/T7VHUVzn
Complete (Done) | Player Ability - Capture Grenade | If a grenade has landed but not yet exploded, the player can pick it up and add it to their own reserve of grenades. | 5 |  | CL | Low Priority | 7 | https://trello.com/c/Vqj2pzRv
Complete (Done) | Identifiable icon | Intent: - Allow users to easily recognize the game from its icon image Note on estimation: - There should be very little time needed to complete this task. Adding an icon tot he game's exe using unity involves a drag and drop in the player settings. | 0.5 |  | RW | TRC Requirement,Medium Priority | 9 | https://trello.com/c/bgRBJONX
Complete (Done) | Level Transition | Smooth transitions for game play | 3 |  | KT | Medium Priority | 15 | https://trello.com/c/5SyYA3Od
Complete (Done) | Level 3 | Defeat the terrorist boss and his minions to win the game | 13 |  | T | High Priority | 11 | https://trello.com/c/TB6KCrZ8

## Archived 4 Beta Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Sprint Backlog (Beta) | [archived] Play the game using an android device | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Make the game playable on an android tablet If the game supports the tablet as its target platform. - If you have not already installed the packages necessary to export android build you can follow the directions how to do so here https://www.youtube.com/watch?v=4YNH9Y7NR3U |  |  |  | TRC Requirement,Target Platform | 14 | https://trello.com/c/S0YIR8DN
Sprint Backlog (Beta) | [archived] Controls function and be comfortable when playing the game on an android device | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Customize the player controls for a touch-based device if the game supports the tablet as its target platform. |  |  |  | TRC Requirement,Target Platform | 15 | https://trello.com/c/izn8asAz
Sprint Backlog (Beta) | [archived] Update Tutorial ui | [5 empty] | 1 | https://trello.com/c/yubuWm1G